## About
London Reporting Academy
Guide | First ESRS Reporting Cycle: A 15-Month Project Plan for Companies and Groups
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/esrs/esrs-reporting-cycle-and-controls/first-esrs-reporting-cycle-a-15-month-project-plan-for-companies-and-g/
Standard edition | ESRS 2023 legal baseline and Commission-adopted revised ESRS 2026, with explicit version gate
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-10
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Type
Type
Type | Tier | Audience — Current context
First-cycle implementation and resource planning guide | Tier 3 · Deep Project Guide | Project sponsors, CFOs, sustainability leads, group reporting, legal, risk, internal control, internal audit and assurance teams — Commission-adopted revised ESRS 2026 and first-cycle implementation considerations checked to 2 August 2026

## Months
Months
Months | Workstream and core actions | Controlled output / gate
M1-M2 | Confirm legal scope, reporting period, individual or consolidated basis, applicable ESRS version, national requirements, filing location, assurance requirement and governance. Appoint sponsor, programme lead, workstream owners and technical reviewer. | Approved scope memo, version decision, governance charter, RACI, budget, board calendar and issue escalation route.
M2-M4 | Map strategy, business model, legal entities, activities, sectors, products, geographies, upstream/downstream relationships, existing due diligence, stakeholder processes, risk registers and public commitments. | Controlled business-model/value-chain map, evidence inventory, source register and population of potential IRO signals.
M3-M6 | Design and perform the DMA. Identify and assess impacts, risks and opportunities; use stakeholder and expert evidence; set thresholds; challenge severe-impact coverage; validate and approve conclusions. | Approved methodology, IRO register, evidence register, material topics/sub-topics and governance minutes.
M4-M8 | Create the disclosure architecture. Map material IROs to ESRS 2, topical DRs/ARs, GDR-P/A/M/T and entity-specific needs. Assign owners and define narrative and metric outputs. | Disclosure matrix, data-request catalogue, content plan, source anchors and information-materiality decision log.
M5-M9 | Design metrics and data controls. Fix definition, unit, boundary, calculation, source, estimates, value-chain method, evidence, comparatives, change control and review. Issue group instructions. | Approved data dictionary, methodology files, control matrix, evidence standard, consolidation instructions and dry-run template.
M7-M11 | Collect dry-run and in-period data; perform calculations and estimates; reconcile entity submissions; investigate exceptions; draft policies, actions, metrics, targets and financial-effect narratives. | Dry-run pack, unresolved-gap log, calculation files, review evidence, first full narrative draft and financial connectivity map.
M10-M13 | Operate controls and prepare for assurance. Freeze key methods, test populations and access, review evidence, challenge estimates, run disclosure and consistency reviews, prepare assurance requests and remediation. | Assurance-ready evidence index, control results, corrected exceptions, management review pack and near-final statement.
M13-M15 | Complete period-end data, comparatives and events after reporting period; finalise digital output and management report; obtain committee/board approvals; sign management representations; publish and archive. | Approved sustainability statement, assurance report, digital/tagged output as applicable, publication record, archive and next-cycle improvement plan.

## Critical dependency
Critical dependency
Critical dependency | Why it blocks later work | Early control
Legal scope and standard version | Determines entity population, basis of preparation, group instructions, assurance and public statement. | Written legal/accounting scope decision, explicit assumptions and trigger for reassessment.
Reporting boundary and value-chain map | Metric population and IRO identification cannot be stabilised without knowing what operations and relationships are relevant. | Reconcile to financial consolidation, legal entities, operations and significant business relationships.
DMA conclusions | Disclosure matrix, data requests and narrative cannot be finalised if material IROs and sub-topics remain open. | Time-box evidence collection, establish challenge gates and escalate unresolved severe impacts.
Metric definitions and methods | Late method changes create inconsistent subsidiary submissions, restatements and assurance gaps. | Approve methods before the main collection cycle and run a dry calculation.
Data-owner capacity and system access | A theoretically sound method fails when the population cannot be extracted, reviewed or evidenced. | Name deputies, test access, sample source records and agree cut-off rules.
Financial effects and connected information | Sustainability and financial narratives can contradict each other if finance joins late. | Create a joint finance-sustainability issue list and reconciliation control.
Assurance access and remediation time | Late evidence requests can expose gaps after the board timetable is fixed. | Agree scope, evidence protocol and milestone reviews early while preserving management responsibility.
Governance approval | The statement cannot be responsibly released if material judgements and limitations were not escalated. | Schedule methodology, materiality and final publication gates in the board calendar from M1.

## Role resource
Role / resource
Role / resource | Illustrative first-cycle assumption | Comments
Executive sponsor | 0.05-0.10 FTE over the programme | Removes blockers and owns major governance decisions; not the day-to-day project manager.
Programme lead / reporting owner | 0.8-1.0 FTE during design and close; 0.5-0.8 between peaks | Controls scope, plan, issue log, statement and approvals.
Technical ESRS lead | 0.5-1.0 FTE depending on complexity | Maintains source set, methodology, requirement mapping and technical review.
DMA workstream | 2-5 core contributors over M2-M6 plus subject experts | Sustainability, risk, legal, operations, HR, procurement, finance and stakeholder expertise.
Data and controls team | 1-4 FTE equivalent plus distributed data owners | Depends heavily on number of metrics, systems and group entities.
Finance and financial effects | 0.3-1.0 FTE equivalent across FP&A, accounting and treasury | Needed for connectivity, financial effects, CapEx/OpEx and consistency.
Legal / compliance | 0.2-0.6 FTE equivalent plus targeted specialist review | Scope, claims, omissions, due diligence, contracts and sensitive information.
Group / subsidiary coordinators | Typically 0.1-0.4 FTE per significant reporting unit during collection peaks | Local collection, evidence, validation, explanation and sign-off.
Internal control / internal audit | Targeted design review and pre-assurance testing | Should challenge control design without taking management ownership.
External specialist support | Flexible, concentrated on technical gaps and surge periods | Useful for DMA facilitation, GHG, scenario analysis, nature, human rights, data models or technical review.

## Decision output
Decision / output
Decision / output | Board or committee | CFO / sponsor — Reporting lead — Functional owner — Legal / control / assurance
Legal scope and version | I / oversight | A — R — C — C / legal advice
DMA methodology and conclusions | A / oversight | C — R — C — C / challenge
Metric definitions and methods | I | A — R — R — C / control review
Data submission and evidence | I | C — A — R — C / test
Narrative and financial connectivity | C | A — R — R — C
Reliefs, omissions and significant limitations | A for significant matters | C — R — C — C / legal-assurance review
Final statement and publication claim | A | R — R — C — C; assurance concludes only within engagement scope

## Source
Source
Source | Role in this article | Official link
European Commission, Commission Delegated Regulation C(2026) 5010 and annexes, 3 July 2026 | Commission-adopted revised ESRS text, explanatory memorandum, application and transition context | Open source
Commission Delegated Regulation (EU) 2023/2772 | Current ESRS legal baseline at the source-check date | Open source
European Commission adoption announcement, 3 July 2026 | Adoption and scrutiny status of revised ESRS | Open source
Commission-adopted revised ESRS annex, 3 July 2026 | Primary requirements for materiality, boundaries, preparation, presentation and general disclosures | Open source
CEAOB guidelines on limited assurance, 30 September 2024 | Transitional high-level assurance context; subject to national rules and engagement terms | Open source
Accounting Directive, consolidated 18 March 2026 | EU legal framework for sustainability reporting and assurance | Open source

## Instrument requirement
Instrument / requirement
Instrument / requirement | Relationship | Role and limitation
Accounting Directive and national law | Legal context | Scope, management-report location, governance and assurance requirements.
Revised ESRS 1 | Direct | Boundary, double materiality, information materiality, presentation, comparatives and reliefs.
Revised ESRS 2 BP, GOV, SBM and IRO | Direct | Basis, governance, strategy, materiality process and disclosure architecture.
Revised ESRS 2 GDR-P/A/M/T | Implementation | Policies, actions, metrics and targets workstreams.
CEAOB limited-assurance guidelines / national pronouncements | Assurance context | Risk-based preparation; not a substitute for engagement terms or national rules.