## About
London Reporting Academy
Guide | First EU Voluntary Reporting Cycle: A 90-Day and 12-Month Roadmap
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/eu-voluntary/eu-voluntary-preparing-the-report/first-eu-voluntary-reporting-cycle-a-90-day-and-12-month-roadmap/
Standard edition | —
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Table 1
Track | Purpose | Best output
90-day track | Create a first controlled response or report. | Report skeleton, completed core datapoints, evidence register, gap log and release decision.
12-month track | Make the process repeatable. | Quarterly data routine, improved methodology, owner network, response history and next-cycle controls.

## The 90-day roadmap
The 90-day roadmap
Period | Main actions | Output
Days 1-15: scope and purpose | Classify requesters, decide reporting period, legal entity or group basis, module option and intended outputs. | Scope note and project charter.
Days 16-30: datapoint map | Map B1-B11 and, where relevant, C1-C9 to owners, systems and evidence sources. | Applicability matrix and owner list.
Days 31-45: data collection | Collect general information, energy, GHG, pollution, biodiversity, water, waste, workforce, safety, pay, governance and policy information. | Minimum dataset with evidence IDs.
Days 46-60: gaps and estimates | Classify missing items as unavailable, estimated, not applicable, voluntary or omitted under a permitted basis. | Gap log and estimation methodology.
Days 61-75: drafting | Prepare the report, counterparty pack or lender pack using approved wording and cross-references. | Draft output and disclosure index.
Days 76-90: review and release | Run technical, legal/confidentiality and management review; approve release version and response history. | Final first-cycle output and improvement plan.

## The 12-month roadmap
The 12-month roadmap
Quarter | Focus | Practical result
Q1 after release | Post-cycle lessons. | List of data gaps, slow owners, weak definitions and request pain points.
Q2 | System and evidence design. | Updated data dictionary, folder structure, release rules and training for owners.
Q3 | Interim data refresh. | Partial update of energy, HR, incident, policy and request-response data.
Q4 | Pre-close readiness. | Known estimates, year-end evidence plan, review calendar and publication decision.
Next cycle | Controlled repeat. | Comparatives, fewer manual gaps and a clearer claim about the selected option.

## Table 4
Gap type | Meaning | First-year response
Not applicable | The condition for the datapoint is not met. | Record the reason and retain evidence.
Unavailable | The datapoint applies but data is not yet available. | Disclose limitation where relevant and create an improvement action.
Estimated | Data is available only through a reasonable method or assumption. | Document methodology, inputs and review.
Voluntary non-selection | Information is outside the selected module or voluntary layer. | Record status so users do not mistake it for missing data.
Confidential omission | Information is withheld under a permitted basis. | Record rationale, approval and disclosure of the use of exemption where required.

## Common planning mistakes
Common planning mistakes
Mistake | Consequence | Fix
Starting with design rather than data | Beautiful report with weak evidence. | Build dataset and evidence first, then design output.
Trying to complete every possible datapoint | Slow, expensive and confusing. | Start from selected option, purpose and applicable datapoints.
Waiting for perfect data | No useful response to market requests. | Classify gaps and publish a controlled limitation where appropriate.
No release decision | Public, lender and customer versions diverge. | Define outputs and audiences early.
No 12-month owner | Next year becomes another emergency project. | Assign ongoing owner and quarterly rhythm.