## About
London Reporting Academy
Guide | First GRI Report in 90 Days: What Is Realistic and What Must Wait
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/gri/gri-evidence-controls-and-assurance/first-gri-report-in-90-days-what-is-realistic-and-what-must-wait/
Standard edition | —
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Final 90-day readiness checklis
Final 90-day readiness checklist
From: First GRI Report in 90 Days: What Is Realistic and What Must Wait
# | Check | Status | Owner | Evidence / note
1 | • ☐ Executive sponsor, reporting owner, working group and final approver are named.
2 | • ☐ Reporting organisation, period, entities, sites and major boundary differences are approved.
3 | • ☐ Applicable Sector Standards and current Topic Standard editions have been checked.
4 | • ☐ Impact inventory covers actual/potential and positive/negative impacts across activities and relevant business relationships.
5 | • ☐ Stakeholder, due-diligence, incident, grievance and external evidence are retained and limitations are explicit.
6 | • ☐ Significance criteria, threshold or prioritisation logic and human-rights treatment are documented.
7 | • ☐ Material topics and changes from the prior period are formally approved.
8 | • ☐ GRI 3-3 and relevant Topic Standard information are traceable to evidence and owners.
9 | • ☐ GRI 2 disclosures and Content Index references are reviewed at requirement level.
10 | • ☐ Estimates, reasons for omission, confidentiality and unavailable information have approved wording.
11 | • ☐ Technical findings and cross-publication contradictions are resolved.
12 | • ☐ The statement of use matches the requirements actually met.
13 | • ☐ Governance approval, version lock, publication files and evidence archive are complete.
14 | • ☐ Next-cycle actions have owner, budget or resource path and deadline.

## FORMAT
FORMAT
FORMAT | LANGUAGE | VERSION
Planning Guide | British English | 1.0 • 1 August 2026

## When a 90-day project is realis
When a 90-day project is realistic
Enabling condition | Why it matters | Early evidence
Executive sponsor and empowered reporting owner | Scope, resources and disagreements can be resolved within days rather than weeks. | Named sponsor, project charter and decision calendar.
Stable reporting organisation and period | The team can define entities and reporting boundary without reopening the project repeatedly. | Legal entity list, financial reporting perimeter and approved sustainability boundary principles.
Existing policies, data and operational records | GRI disclosures can be supported from real source evidence rather than created retrospectively. | Prior report, HR/operations/environmental datasets, governance minutes, policies and complaint records.
Responsive cross-functional working group | Data owners can answer technical questions and approve wording quickly. | Confirmed roles, weekly meeting and escalation route.
Focused but credible impact assessment | The organisation can build from due diligence, incidents, stakeholder evidence and previous work while addressing known gaps. | Impact universe, existing risk/impact studies, complaints, audits, media/NGO evidence and stakeholder channels.
Disciplined publication scope | The team is willing to publish a proportionate first output and state gaps instead of filling every desired chapter. | Approved page architecture, material-topic scope and deferred-content list.
No dependency on immediate external assurance | The timetable is not contingent on procuring, scoping and completing assurance without readiness. | Separate assurance-readiness plan and accurate wording.

## Minimum credible output versus
Minimum credible output versus work that must wait
Can be achieved in a controlled 90-day cycle | Must not be shortened into a false conclusion
Approved project scope, reporting organisation, reporting period and working governance. | Resolution of a disputed legal boundary or complex joint-venture control question without evidence and approval.
A documented impact inventory drawing on existing operational, due-diligence, stakeholder and external evidence. | A complete understanding of affected people and severe human-rights impacts where meaningful engagement or specialist review has not occurred.
A focused significance assessment, calibrated criteria and an approved list of material topics. | Mechanical scoring or management override designed to exclude difficult impacts.
GRI 2, GRI 3 and selected/applicable topic disclosures supported by available evidence. | Invented data, unsupported narrative, retrospective policies or ‘not applicable’ labels for processes that do not exist.
A requirement-level Content Index with precise references and transparent omissions or limitations under the applicable route. | A Content Index that implies complete disclosure when references are broad, inaccessible or partial.
Internal technical review, consistency checks, management sign-off and a next-cycle remediation plan. | External assurance, legal opinion or board approval without sufficient review time and evidence.
A clear decision between in accordance, with reference and deferred claim. | An in-accordance statement based on effort, intention or the presence of a GRI logo.

## The 13-week accelerated roadmap
The 13-week accelerated roadmap
Week | Primary work | Key output — Decision owner
1 | Mobilise: confirm sponsor, reporting owner, working group, timetable, version control and reporting-route decision criteria. | Project charter, RACI, source request and decision calendar. — Executive sponsor / reporting owner.
2 | Lock initial scope: reporting organisation, period, entity/site population, acquisitions/disposals, applicable Sector Standards and known constraints. | Boundary memo, entity/site register and applicability log. — Reporting owner with finance/legal input.
3 | Build impact universe from operations, value chain, due diligence, incidents, grievances, stakeholder evidence, external sources and prior assessments. | Impact inventory and evidence register. — Materiality lead and functional owners.
4 | Assess actual/potential, positive/negative impacts; apply severity, likelihood and human-rights logic; record uncertainty. | Scored or tiered impact assessment with rationale and exceptions. — Materiality working group.
5 | Calibrate criteria and threshold; challenge omissions; test Sector Standard likely material topics; identify evidence gaps. | Calibration record, decision log and provisional topics. — Technical lead / management sponsor.
6 | Validate and approve material topics; define topic boundaries, owners, applicable Topic Standards and disclosure plan. | Approved GRI 3-2 list and disclosure applicability matrix. — Authorised management or governance body.
7 | Prepare GRI 2 and GRI 3-1/3-2 disclosures; launch topic-specific data requests and GRI 3-3 drafting. | Universal Standards draft and controlled data-request tracker. — Reporting owner and data owners.
8 | Prepare topic metrics, methodologies, limitations and evidence; identify required reasons for omission where permitted. | First topic disclosure pack and estimate/gap log. — Data owners and technical reviewers.
9 | Complete GRI 3-3 for each material topic; reconcile policies, actions, effectiveness and stakeholder engagement with metrics. | Integrated topic packs and evidence map. — Topic owners / reporting team.
10 | Assemble draft report and requirement-level Content Index; test references, accessibility and reporting claim. | Controlled draft and Content Index version 0.9. — Editor / reporting owner.
11 | Technical red-team and consistency review across annual report, website, policies and public claims; resolve critical findings. | Findings log, corrected draft and go/no-go recommendation. — Independent technical reviewer.
12 | Management and governance approval; finalise limitations, statement of use, publication note and remediation plan. | Approved final content and signed control pack. — Executive sponsor / governance body.
13 | Lock version, publish or defer, notify relevant stakeholders, archive evidence and open next-cycle actions. | Published package or documented no-go decision; next-cycle roadmap. — Final approver / publisher.

## Five gono-go gates
Five go/no-go gates
Gate | Timing | Pass criteria — No-go action
G1 — Scope and route | End of Week 2 | Reporting organisation, period, applicable standards, preliminary route and approvers are defined. — Escalate unresolved scope; do not launch broad drafting or promise a claim.
G2 — Impact evidence | End of Week 5 | Impact universe covers operations and relevant business relationships; significance logic and major gaps are documented. — Extend evidence work, narrow publication ambition or defer materiality conclusion.
G3 — Material topics and owners | End of Week 6 | Final topics, rationale, approval, topic owners and disclosure applicability are recorded. — Do not present a provisional management list as approved material topics.
G4 — Disclosure traceability | End of Week 11 | Critical disclosures, calculations, limitations and Content Index references can be traced to evidence; no unresolved blocker. — Revise route, remove unsupported claim, disclose permitted omission or delay publication.
G5 — Governance and release | End of Week 12 | Approvals, statement of use, final version, legal/confidentiality review and publication controls are complete. — Do not publish until accountable approval and version control are complete.

## How to choose the reporting rou
How to choose the reporting route at the end of the project
Route | Use when | Minimum publication discipline — Red flag
Report in accordance with the GRI Standards | All applicable GRI 1 requirements are met, including required Universal, Sector and relevant Topic Standard treatment, Content Index and statement of use. | Requirement-level completion test, permitted omissions only where conditions are met, accurate statement of use and final approval. — Management equates substantial completion with full in-accordance eligibility.
Report with reference to the GRI Standards | The organisation uses selected Standards or disclosures for a clearly defined purpose but cannot or does not seek to meet all in-accordance requirements. | State precisely which GRI Standards/disclosures are used, prepare the applicable Content Index information and avoid broader compliance language. — The report is marketed as a full GRI report despite a limited selection.
Defer the public GRI claim | Materiality, boundary, evidence or governance gaps are so significant that either route would mislead readers. | Publish a non-GRI sustainability update if appropriate, or delay; retain the internal gap and remediation plan. — Deadline pressure is treated as a reason to invent evidence or obscure uncertainty.

## Table 7
Weak project conclusion | Stronger project conclusion
“We completed a comprehensive GRI-compliant report in twelve weeks.” | “During the 13-week first cycle, we established the reporting boundary, assessed impacts using operational, workforce, grievance, stakeholder and external evidence, and approved five material topics. The publication uses specified GRI 2, GRI 3 and Topic Standard disclosures with reference to the GRI Standards. Supply-chain impact evidence is currently limited to priority procurement categories and country-level screening; supplier-level assessment and additional metrics are scheduled for the next cycle. The report has not been independently assured.”