## About
London Reporting Academy
Guide | First IFRS S1 and S2 Reporting Cycle: A 12-Month Implementation Plan
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/ifrs-issb/ifrs-issb-choosing-topics-and-metrics/first-ifrs-s1-and-s2-reporting-cycle-a-12-month-implementation-plan/
Standard edition | —
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## 12-month implementation checkli
12-month implementation checklist
From: First IFRS S1 and S2 Reporting Cycle: A 12-Month Implementation Plan
# | Check | Status | Owner | Evidence / note
1 | Month 1: approve the reporting basis, editions, relief decisions, governance, RACI and programme controls.
2 | Month 2: build the risk and opportunity universe using reasonable and supportable information and the IFRS S1 source hierarchy.
3 | Month 3: document material information decisions and create the first disclosure architecture and matrix.
4 | Month 4: assess climate risks and opportunities and design commensurate scenario analysis.
5 | Month 5: connect strategy, scenarios and risks to budgets, forecasts, financial effects, accounting and funding.
6 | Month 6: approve metrics, targets, data dictionary, evidence register and industry-based requirements.
7 | Month 7: run the GHG and metric dry close, including Scope 3 category screening and amendment assessment.
8 | Month 8: operate disclosure controls, test evidence and agree assurance scope where relevant.
9 | Month 9: complete the full draft, matrix, cross-references and technical red-team review.
10 | Month 10: perform the hard close, reconciliations, comparative analysis and late-adjustment control.
11 | Month 11: resolve independent-review findings and obtain committee and board approval.
12 | Month 12: publish on the required basis, archive the evidence package and launch the next cycle.

## Table 1
Critical-path dependency | Why it controls the timetable | Parallel work that can continue
Reporting basis and applicable edition | Determines period, claim, reliefs, comparatives and amendment status | Preliminary source inventory and stakeholder scheduling
Risk and opportunity universe | Determines which topics, value-chain areas and data streams require assessment | Governance evidence and existing metric inventory
Materiality decisions | Determine the disclosure architecture and depth | Technical data collection for likely high-priority areas
Climate resilience and financial effects | Influence strategy narrative, forecasts, accounting cross-check and board decisions | GHG calculations, industry metric definitions and control design
Evidence and controls | Determine whether the disclosure is supportable and assurance-ready | Drafting of stable sections and design work
Final completeness and compliance conclusion | Determines whether the proposed claim can be made | Publication formatting, digital tagging and communication planning

## Recommended programme cadence
Recommended programme cadence
Forum | Frequency | Purpose — Core record
Workstream meeting | Weekly during active phases | Complete tasks, resolve technical dependencies and update evidence — Action log and workstream dashboard
Technical decision forum | Fortnightly or as needed | Approve judgements on scope, materiality, methods, reliefs and wording — Judgement register and decision paper
Programme steering committee | Monthly | Review critical path, resources, blockers, assurance and board readiness — Integrated status and risk report
CFO / executive sponsor review | At key gates | Approve finance assumptions, reporting basis and escalation — Gate sign-off
Board or committee updates | At least quarterly in first cycle | Build oversight evidence and avoid a single late approval event — Board papers and minutes
Dry run / hard close | At M7 and M10 in this model | Test operation, evidence, controls and final data — Close pack, exceptions and remediation

## Table 3
Transition provision | Practical decision | Control implication
IFRS S1 E3 | No comparative information is required in the first annual reporting period of initial application | Decide whether voluntary comparatives will be provided and ensure they are not misleading
IFRS S1 E4 | First-year sustainability disclosures may be reported after the related financial statements within the specified interim-report or nine-month timing | Confirm jurisdiction permits the relief, publication date and communication plan
IFRS S1 E5-E6 | First-year reporting may be limited to climate-related risks and opportunities, with related comparative relief in the second year | Disclose use, plan non-climate implementation and track second-year comparative requirements
IFRS S2 C3 | No comparative IFRS S2 information is required before initial application | Document comparative starting point and any voluntary data
IFRS S2 C4 | Specified first-year reliefs may be available for a pre-existing non-GHG-Protocol method and Scope 3 emissions | Document eligibility, disclosure and system migration plan
IFRS S2 2025 amendments | Mandatory for periods beginning on or after 1 January 2027; earlier application permitted | Approve early-adoption decision, update methods, classifications, controls and comparatives

## Common first-cycle mistakes
Common first-cycle mistakes
Mistake | Why it delays the cycle | Correction
Starting with the report template | Scope, materiality and evidence decisions are hidden inside drafting | Lock reporting basis and risk universe before detailed prose
Treating materiality as a one-day workshop | Value-chain, industry and financial evidence is incomplete | Use a documented multi-source assessment and review significant judgements
Leaving SASB until the metric stage | Industry risks and disclosures may be identified too late | Refer to and consider SASB during risk/opportunity identification and metric selection
Starting Scope 3 after year end | Data collection, estimation and category screening have long lead times | Run a complete dry close several months before year end
Running scenarios separately from finance | Strategic implications and financial effects cannot be connected | Create a common assumption and decision bridge
Assuming a transition relief solves the underlying system gap | The next cycle inherits an undocumented dependency | Use a relief register with expiry, owner and remediation plan
Obtaining assurance too late | Evidence formats and control gaps emerge after close | Agree scope and evidence expectations during control design
Treating publication as project closure | No archive, update trigger or second-year comparative plan exists | Complete post-implementation review and launch the next cycle