## About
London Reporting Academy
Guide | How to Prepare for UAE Climate Law Compliance: Step-by-Step MRV Roadmap
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/uae/uae-ghg-inventory/how-to-prepare-for-uae-climate-law-compliance-step-by-step-mrv-roadmap/
Standard edition | —
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Pre-submission checklist
Pre-submission checklist
From: How to Prepare for UAE Climate Law Compliance: Step-by-Step MRV Roadmap
# | Check | Status | Owner | Evidence / note
1 | The entity, facility, emirate, free-zone status and potential reporting instruments have been recorded.
2 | The relevant authority and current reporting route have been confirmed or an unresolved query is visible.
3 | The boundary memorandum explains organisational, operational, metric and authority-specific differences.
4 | The source register reconciles to facilities, equipment, permits, purchases and processes.
5 | Every method, factor, conversion, estimate and material change is controlled and reproducible.
6 | Data owners, reviewers, approvers, evidence custodians and release authority are named.
7 | The inventory is tied to original evidence and significant movements have been challenged.
8 | The five-year federal record-retention requirement and any longer local requirement are addressed.
9 | Verification expectations have been identified for the applicable instrument; readiness is not described as assurance.
10 | Current and planned reduction measures are linked to sources, expected results, owners and evidence.
11 | Management and the board or delegated committee have approved the basis, limitations and release.
12 | The portal receipt, signed report, calculation version and correspondence will be retained as one release pack.

## Article map
Article map
Stage | What the reader will be able to do
Answer | Explain why a regulator-controlled applicability and authority record comes before calculation.
Design | Build the boundary, source register, methodology, RACI, calculation and evidence architecture.
Operate | Run a pilot inventory, resolve gaps, prepare for verification and connect emissions to reduction measures.
Approve | Create a board-ready basis, limitations note, release decision and next-cycle improvement plan.
Control | Use a 6-12 month roadmap without confusing project timing with a statutory reporting calendar.

## Table 2
Applicability record | Minimum content | Control evidence
Entity and licence facts | Legal name, trade licence, branch/subsidiary status, free zone or mainland, responsible signatory. | Current licence, legal structure chart and authority correspondence.
Facility facts | Location, operator, ownership/control, processes, meters, permits, landlord arrangements and outsourcing. | Facility register, site map, permits, contracts and meter responsibility matrix.
Potential legal route | Federal Climate Law, Article 6 designation, Resolution 67 registry test, local MRV, permit or sector rule. | Instrument-and-version register with source link and applicability conclusion.
Authority route | Who sets the method, receives data, verifies accuracy, inspects and decides or hears a challenge. | Authority register, named contacts, written response and follow-up date.

## Table 3
Source-register field | Why it matters | Typical evidence
Source ID and description | Prevents duplicate or missing sources and supports year-on-year change control. | Equipment register, process map, permits and engineering records.
Facility and boundary status | Shows whether the source belongs to this entity, facility or reporting route. | Boundary memorandum and facility register.
Activity data and unit | Defines what is measured and avoids mixed-unit calculations. | Invoices, meter exports, fuel logs, production systems and maintenance records.
Factor and method | Makes the calculation reproducible and identifies authority-specific requirements. | Approved methodology, factor register and calculation specification.
Owner and reviewer | Creates accountability and segregation between preparation and challenge. | RACI, control matrix and sign-off record.
Data-quality status | Identifies estimates, missing periods, uncertainty and improvement priority. | Gap log, estimate note and remediation action.

## Table 4
Role | Core responsibility | Do not confuse with
Executive sponsor | Resources, cross-functional authority and escalation. | Technical approval of every factor or calculation.
Reporting owner | Boundary, calendar, consolidation, status control and submission coordination. | Ownership of all underlying operational data.
Data owner | Completeness and accuracy of source-system records. | Final approval of the public or regulatory submission.
Method owner | Method specification, factors, assumptions and changes. | Independent verification.
Reviewer | Recalculation, reconciliation, challenge and issue closure. | Reperforming preparation without documented challenge.
Board / delegated committee | Approval of basis, key judgement, limitations, reduction plan and release authority. | Day-to-day data collection.

## Table 5
Control objective | Example control | Evidence of operation
Completeness | Reconcile the source register to facilities, permits, equipment and general-ledger or procurement populations. | Signed reconciliation and unresolved-source log.
Accuracy | Recalculate material sources; compare factors and conversions to the approved register. | Reviewer worksheet and factor check.
Cut-off | Test invoice, meter and production periods against the reporting period. | Cut-off schedule and exception resolution.
Change management | Approve boundary, method, factor, system and estimation changes before use. | Change request, impact assessment and approval.
Access and retention | Restrict editing, retain released evidence and make it retrievable for at least the applicable period. | Access report, repository index and retention policy.
Submission integrity | Compare the approved report or portal entry to the signed calculation and narrative pack. | Final tie-out and portal receipt.

## Table 6
Reduction-plan element | Strong record | Weak shortcut
Measure | Specific operational or technology change linked to an emission source. | “Improve sustainability” without source or action.
Expected result | Quantified or clearly qualitative result with method and timing. | Unexplained percentage detached from inventory boundary.
Dependency | Grid, supplier, technology, permit, capital, data or operational dependency. | Assuming implementation is entirely within management control.
Progress evidence | Purchase order, commissioning record, meter trend, project gate or verified operational data. | Treating a board-approved intention as completed action.
Governance | Owner, budget status, decision gate and escalation. | No accountable owner or review cadence.

## A practical 6-12 month programm
A practical 6-12 month programme
Phase | Main actions | Exit evidence — Primary owner
Month 0-1: mobilise | Sponsor; entity/facility map; legal and authority scan; preliminary emissions estimate; authority register. | Approved scope of project, responsibility map and open regulator questions. — Executive sponsor + legal/compliance.
Month 1-3: define | Boundary memorandum; source register; method and monitoring plan; data-owner RACI; reporting calendar. | Approved boundary, source population and method specifications. — Reporting owner + facility/method owners.
Month 3-5: build | Data extracts; calculation model; factor register; evidence repository; completeness and accuracy controls. | Reproducible draft inventory and evidence index. — Data owners + finance/internal control.
Month 5-7: dry run | Pilot close; variance review; estimate approvals; issue log; draft authority submission; reduction options. | Dry-run findings and prioritised remediation plan. — Reporting owner + reviewers.
Month 7-9: challenge | Internal technical review; legal/status check; verifier engagement where applicable; correction closure. | Signed findings, corrected inventory and controlled draft. — Independent reviewer / verifier where applicable.
Month 9-12: approve and improve | Final tie-out; board paper; filing or response; reduction plan; lessons learned; next-cycle calendar. | Approved submission pack, receipt, reduction roadmap and control improvements. — Board sponsor + reporting owner.

## Weak versus stronger implementa
Weak versus stronger implementation
Area | Weak approach | Stronger approach
Applicability | Assume every group entity has the same duty because the law is federal. | Record entity, facility, instrument, authority and written instruction separately.
Boundary | Use the financial consolidation perimeter without testing facility or registry rules. | Start from the group, then document every regulatory or metric-specific difference.
Methods | Use an online calculator with no controlled factor or version record. | Approve method specifications, factors, units, estimates and change controls.
Evidence | Keep a final spreadsheet and a folder of invoices. | Link each submitted field to evidence, method, review and release approval.
Reduction plan | List aspirations unrelated to the emissions sources. | Link each current or planned measure to the source register, expected result and owner.
Approval | Obtain an email saying “approved”. | Use a board or delegated-committee paper with judgements, limitations and conditions.

## Common mistakes
Common mistakes
Mistake | Why it fails | Correction
Waiting for the first regulator request | The team may have insufficient time to resolve boundary, source and evidence gaps. | Build the controlled foundation now while keeping legal status and deadlines conditional.
Treating 0.5 million tCO2e as the Climate Law threshold | That number belongs to a separate registry instrument and does not define Article 6 designation or local schemes. | Maintain an instrument-specific threshold and trigger register.
Using one group footprint as every regulatory submission | Entity, facility and local reporting routes may differ. | Map one dataset to controlled, instrument-specific outputs.
Calling internal review “verification” | The term may imply a role or conclusion that was not performed. | Name the actual procedure, provider, scope and output.
Keeping only the final value | A number without boundary, method, source and control evidence is difficult to defend. | Retain the full data lineage and release version.