## About
London Reporting Academy
Guide | First UAE MRV Reporting Cycle: legal route, boundaries, facilities, methods, data controls, dry runs, verification, board approval and filing
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/uae/uae-governance-and-carbon-claims/first-uae-mrv-reporting-cycle-legal-route-boundaries-facilities-method/
Standard edition | —
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Twelve-month readiness checklis
Twelve-month readiness checklist
From: First UAE MRV Reporting Cycle: legal route, boundaries, facilities, methods, data controls, dry runs, verification, board approval and filing
# | Check | Status | Owner | Evidence / note
1 | Legal routes and designation status are reviewed and approved.
2 | Authority contacts and material questions are logged.
3 | Entities, facilities, operators and emission sources are reconciled.
4 | Methods, factors, units, GWP and estimates are controlled.
5 | Original evidence and five-year retention are tested.
6 | Recurring controls operate before the final close.
7 | A pilot inventory is independently recalculated.
8 | Reduction, adaptation, credits and claims are reconciled.
9 | Verification status, competence and conflicts are confirmed.
10 | Board representations, final file, receipt and checksum are retained.

## Table 1
Month | Primary objective | Main output — Control gate
1 | Legal route and status | Dated applicability memorandum — Legal approval
2 | Authority engagement | Questions log and confirmed contacts — No undocumented material assumptions
3 | Entity, facility and source mapping | Reconciled source register — Operations sign-off
4 | Methods and factors | Monitoring/method plan — Technical approval
5 | Data and evidence design | Data dictionary and evidence matrix — Ownership and retention test
6 | Internal controls | Control register and close calendar — Segregation and review
7 | Pilot close | Trial inventory and issue log — Recalculation and completeness
8 | Reduction and adaptation plans | Action, risk and finance bridge — Gross/credit separation
9 | Internal review | Findings and retest plan — Critical issues escalated
10 | Verification readiness | Verifier pack or equivalent review — Competence and conflict checks
11 | Board approval | Board paper and representations — Approved limitations and claims
12 | Filing and retention | Submitted file, receipt, checksum and archive — Final-file control

## First-cycle RACI
First-cycle RACI
Workstream | Responsible | Accountable — Consulted — Evidence of completion
Legal route | Legal/compliance | General counsel or accountable executive — Sites, sustainability, external counsel — Approved applicability memorandum
Sources and data | Site/operations owners | Operations executive — MRV team, procurement, IT — Reconciled source register
Methods | Technical/MRV lead | CFO or designated executive — Authority, verifier, engineering — Approved method register
Controls | Finance/internal control | CFO — Internal audit, IT, sites — Control operation and retest records
Verification | MRV manager | CFO/accountable executive — Procurement, legal, sites — Conflict check, engagement and conclusion
Plans and claims | Strategy/sustainability | Board or delegated committee — Finance, legal, operations — Approved targets, actions and claims ledger
Filing | Authorised submitter | Accountable executive — Legal, finance, MRV — Submitted file, receipt and checksum