## About
London Reporting Academy
Guide | How to Prepare a UK SRS S1 Report: Complete Step-by-Step Guide
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/uk-srs-s1/uk-srs-s1-reporting-cycle-and-publication/how-to-prepare-a-uk-srs-s1-report-complete-step-by-step-guide/
Standard edition | UK SRS S1 (February 2026)
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-10
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## First-cycle readiness checklist
First-cycle readiness checklist
From: How to Prepare a UK SRS S1 Report: Complete Step-by-Step Guide
# | Check | Status | Owner | Evidence / note
1 | The reporting entity, period, standards, route, location and intended claim are approved.
2 | Governance mandates and information flows match the disclosure.
3 | The business model and value chain have been mapped at a decision-useful level.
4 | A complete longlist of climate and other sustainability-related risks and opportunities has been challenged.
5 | Materiality decisions consider nature, magnitude, likelihood, timing, aggregation and obscuring.
6 | UK SRS S2 is integrated, or use of paragraph E3 is explicit and controlled.
7 | Material matters link to strategy, financial effects, metrics, targets and owners.
8 | Industry information and source choices are documented.
9 | Data lineage, methods, estimates, controls and evidence are retained.
10 | Reliefs, limitations, judgements and uncertainty are transparent.
11 | The report has passed technical, finance, legal and red-team review.
12 | Management representations and board approval cover the exact final claim and publication version.

## Table 1
Basis field | Decision to record | Evidence
Reporting entity and period | Group, parent-only or other permitted reporting entity; period aligned to financial statements | Consolidation map, reporting calendar, finance sign-off
Standards and edition | UK SRS S1 and S2 issued February 2026; any other basis separately identified | Controlled source register and version record
Reporting route | Voluntary application or specific future legal/regulatory route | Legal and regulatory applicability note
Claim | Full compliance, UK SRS S2 compliance with disclosed relief, or scoped reference wording | Claim decision and approval record
Reliefs and limitations | E3 and any other reliefs, data limitations and transition decisions | Relief register and remediation plan

## Table 2
Pillar | Core work | Evidence retained
Governance | Oversight body, management roles, mandates, skills, information, decision frequency and links to remuneration where relevant | Terms of reference, role descriptions, board papers, minutes, skills assessment
Strategy | Material risks and opportunities, time horizons, business-model and value-chain effects, responses, financial effects and resilience | Strategy papers, plans, scenario records, budget and valuation links, decision log
Risk management | Processes to identify, assess, prioritise, monitor and integrate risks and opportunities | Methodology, criteria, ERM mapping and review records
Metrics and targets | Cross-industry, industry-based and entity-specific metrics; target design and progress | Definitions, methods, source data, reconciliations, target approvals and change records

## Illustrative twelve-month imple
Illustrative twelve-month implementation plan
Month | Primary work | Key output / approval
1 | Confirm reporting basis, standards, reporting entity, period, intended claim and project governance | Approved project charter and Basis of Preparation decision
2 | Map business model, value chain, source universe and existing processes | Value-chain map, source register and gap inventory
3 | Identify climate and other sustainability-related risks and opportunities | Controlled risk and opportunity longlist
4 | Challenge completeness across business units, geographies and time horizons | Revised register and completeness sign-off
5 | Assess investor-focused materiality and approve material matters | Materiality matrix and decision records
6 | Develop governance, strategy, risk-management and S2 workstreams | Four-pillar disclosure plan and climate workplan
7 | Define metrics, targets, industry information and data requests | Metric register and data owner instructions
8 | Build data lineage, evidence files, controls and remediation | Evidence register, control matrix and issue log
9 | Complete current and anticipated financial-effects analysis | Risk-to-finance bridge and finance review
10 | Draft report, Basis of Preparation, reliefs and cross-references | First complete connected draft
11 | Technical, finance, legal, controls and assurance-readiness challenge | Resolved findings and final approval draft
12 | Management representations, committee review, board approval and publication | Approved report, claim and post-publication action plan

## Common mistakes and corrections
Common mistakes and corrections
Mistake | Why it creates risk | Correction
Starting with a disclosure checklist | The population of risks and opportunities may be incomplete | Map the business model and value chain, identify pathways, then assess material information
Treating climate as the whole of S1 without using E3 | The report can omit material non-climate matters and overstate the claim | Either apply full S1 scope or explicitly use and disclose the climate-only provision
Collecting every ESG metric | Cost increases while material information may be obscured | Define metrics from material risks, industry information and decision needs
Separating sustainability from finance until late drafting | Financial effects and planning assumptions become generic or inconsistent | Build a risk-to-finance bridge during assessment and planning
Using polished narrative as evidence | Narrative does not prove the process, data or approval | Retain source, method, owner, review, judgement and approval records
Leaving the compliance claim to the final day | Reliefs and gaps may make the intended wording unavailable | Design the claim and relief register at project inception and reassess throughout