## About
London Reporting Academy
Guide | UK SRS S1 Timeline: 2026 Publication, Proposed 2027 Rules and What Companies Should Do Now
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/uk-srs-s1/uk-srs-s1-voluntary-use-and-mandatory-route/uk-srs-s1-timeline-2026-publication-proposed-2027-rules-and-what-compa/
Standard edition | UK SRS S1 and UK SRS S2, February 2026; current regulatory status reviewed 3 August 2026
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Timeline control checklist
Timeline control checklist
From: UK SRS S1 Timeline: 2026 Publication, Proposed 2027 Rules and What Companies Should Do Now
# | Check | Status | Owner | Evidence / note
1 | Each event is labelled final, current, proposed or future decision.
2 | The entity's accounting period has been mapped to the proposed commencement date.
3 | Current FCA and company-law duties remain in the reporting plan.
4 | The FCA Policy Statement is a formal change-control trigger.
5 | The Companies Act route is tracked separately.
6 | Relief eligibility, duration and claim consequences are not assumed.
7 | The project begins before the reporting period requiring disclosure.
8 | Board, finance, risk, sustainability, legal and data workstreams have dated gates.
9 | Sources and article status will be rechecked before publication.

## Status legend
Status legend
Status | Meaning in this article
Final | Published standard, enacted rule or completed event.
Current | Requirement or policy position operating at the review date.
Proposed | Consultation proposal that can change before finalisation.
Future decision | Government or regulator has announced further work, but no final legal requirement exists.
Company action | Preparation step that can proceed without waiting for regulation.

## The roadmap at a glance
The roadmap at a glance
Date or period | Status | Development — What it means for companies
30 January 2026 | Completed event | FCA published CP26/5 on listed-company UK SRS reporting. — Use the consultation as a planning scenario, not as final law.
25 February 2026 | Final | DBT published final UK SRS S1 and S2 for voluntary use. — Voluntary application can begin; record the intended claim and reporting basis.
20 March 2026 | Completed event | FCA CP26/5 consultation closed. — Monitor the FCA response and final legal instrument.
2026, before final FCA rules | Current | Existing FCA TCFD-aligned rules and current company-law climate duties remain relevant. — Continue current compliance while completing the UK SRS gap assessment.
Autumn 2026 | Proposed milestone | FCA aims to publish a Policy Statement and final rules. — Trigger legal, technical, system and annual-report plan updates immediately after publication.
1 January 2027 | Proposed commencement | FCA proposes the new rules to come into force. — Do not treat this as confirmed until the final Handbook text is issued.
Accounting periods beginning on or after 1 January 2027 | Proposed application | Main in-scope categories would begin UK SRS reporting under the FCA design. — First reports may be published in 2028, depending on the year-end. Preparation must precede the reporting period.
2027 and 2028 periods | Proposed transition | Up to two years of non-climate S1 relief for eligible listed issuers under CP26/5. — Use the period to expand from climate to full material non-climate reporting; disclose use transparently.
Periods beginning on or after 1 January 2029 | Proposed steady state | Proposed non-climate transition relief expired. — Operate full comply-or-explain S1 reporting under the final rule, if adopted as proposed.
Timing to be confirmed | Future decision | Government consideration of Companies Act UK SRS requirements through Modernising Corporate Reporting. — Non-listed entities should monitor separately; scope and timetable may differ from FCA rules.

## Table 3
Proposed year | Non-climate S1 position | Implementation priority
2027 accounting periods | First possible relief year. | Complete the non-climate universe, owners, materiality method and data-gap plan even if publication is deferred.
2028 accounting periods | Second possible relief year. | Run a full dry report, controls test and board review; avoid using the relief as a reason to postpone system design.
2029 accounting periods | Relief proposed to have expired. | Be ready to disclose or explain under the final rule and assess standard-level compliance separately.

## An updateable 12-month preparat
An updateable 12-month preparation plan
Months | Focus | Board or executive gate
1-2 | Regulatory map, scope, project charter and source register. | Approve basis, resources and intended reporting route.
3-4 | Value chain and sustainability risk/opportunity identification. | Challenge completeness and business relevance.
5-6 | Materiality, financial pathways and pillar mapping. | Approve material matters and significant judgements.
7-8 | Metrics, methods, targets, data owners and gap remediation. | Approve target boundaries, methods and priority investment.
9-10 | Draft disclosures, controls testing and finance reconciliation. | Review draft, gaps, estimates and claim options.
11 | Red-team, legal, technical and assurance-readiness review. | Clear critical findings and unresolved explanations.
12 | Annual-report integration, authorisation and evidence archive. | Approve final disclosures, basis and update triggers.

## Common timeline mistakes
Common timeline mistakes
Mistake | Risk | Correction
Treating 1 January 2027 as a confirmed legal date | Plans may be based on consultation text that changes. | Label the date proposed until the Policy Statement and final instrument are issued.
Starting when the reporting period ends | Historical data, controls and governance evidence cannot be reconstructed reliably. | Operate the process during the reporting period.
Assuming first publication is in January 2027 | Application is linked to accounting periods, not immediate publication on commencement day. | Model the entity's actual year-end and authorisation timetable.
Using the proposed relief as a two-year pause | Non-climate systems will still need to be operational when relief expires. | Use relief years for dry runs, remediation and board challenge.
Merging FCA and Companies Act timelines | Scope, legal instruments and transition may differ. | Maintain separate regulatory registers and decision owners.
Forgetting current TCFD duties | A future rule does not excuse current non-compliance. | Preserve current reporting until the rule is formally replaced.