## About
London Reporting Academy
Guide | First UK SRS S2 Reporting Cycle: A 12-Month Implementation Plan
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/uk-srs-s2/uk-srs-s2-cycle-controls-and-assurance/first-uk-srs-s2-reporting-cycle-a-12-month-implementation-plan/
Standard edition | —
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-10
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## First-cycle programme checklist
First-cycle programme checklist
From: First UK SRS S2 Reporting Cycle: A 12-Month Implementation Plan
# | Check | Status | Owner | Evidence / note
1 | The reporting basis, legal status, intended claim and annual-report location are approved.
2 | Every applicable UK SRS S1/S2 requirement has an owner and evidence plan.
3 | Risks and opportunities drive scenario, metric and financial-effects scope.
4 | Scenario sources, assumptions, results, limitations and governance are documented.
5 | Scope 1, 2 and all 15 Scope 3 categories have been considered.
6 | Financed-emissions applicability and any B59A timing issue are addressed.
7 | Industry-based metric sources and non-use decisions are controlled.
8 | Targets have complete baselines, boundaries, milestones and performance data.
9 | Current and anticipated financial effects are linked to finance evidence.
10 | Key controls have operated and significant deficiencies are remediated.
11 | NFSIS, SECR and current FCA obligations are mapped without equivalence claims.
12 | Provisions, judgements, estimates and the compliance statement are approved.
13 | Management, audit committee, board and release gates are complete.
14 | A next-cycle improvement plan and update watchlist are open.

## Table 1
Gate | Question | Typical evidence — Failure response
1. Scope | What entity, period, activity, value-chain population, material matter or metric is covered? | Approved scope memo, entity map, category screen, materiality decision. — Clarify or escalate before data collection expands.
2. Method | What definitions, boundaries, assumptions, factors, models or scenario choices apply? | Methodology, data dictionary, model specification, judgement register. — Return for technical approval or label unresolved judgement.
3. Data | Are sources complete, accurate, timely and version-controlled? | Source register, system extracts, calculation files, estimates and evidence. — Record gap, estimate, late-data procedure or remediation.
4. Control | Have reconciliations, reviews, access controls and issue processes operated? | Control test, reviewer sign-off, exceptions and remediation log. — Do not call the workstream complete; escalate significant deficiency.
5. Disclosure | Does the draft explain the requirement, method, result, change and limitation? | Paragraph-level matrix, narrative, tables, cross-references and claims review. — Revise wording and reconnect to evidence.
6. Approval | Has the accountable owner or governance body approved the conclusion? | Representation, committee paper, minutes and final sign-off. — Return, approve with actions or block release.

## Table 2
Month 1-2 output | Minimum control evidence | Accountable owner
Reporting-basis memorandum | Entity and period reconciliation; legal status; intended claim; location; timetable; provisions considered. | CFO / company secretary
Programme charter and RACI | Named preparers, reviewers, approvers, escalation and decision rights. | Executive sponsor
Requirements and disclosure matrix | Every applicable paragraph, owner, evidence, draft location, status and priority. | Reporting lead
Boundary register | Financial reporting entity, GHG organisational boundary, value chain, targets and metric-specific perimeters. | Finance / sustainability

## Table 3
Milestone | Month | Output — Review question
Scenario design | 2-3 | Method, scope, scenario sources, pathways, time horizons and variables. — Do the selected scenarios test the entity’s material vulnerabilities rather than generic climate themes?
Exposure and vulnerability analysis | 3-4 | Asset, location, product, supplier, customer or portfolio analysis. — Is global scenario information translated to the entity’s facts?
Financial translation | 4-5 | Qualitative pathways, sensitivities or modelled ranges. — Are finance assumptions and scenario assumptions reconciled?
Resilience conclusion | 5-6 | Vulnerabilities, adaptive capacity, options, financial capacity, triggers and uncertainty. — Does the conclusion avoid unsupported “resilient” language?
Governance challenge | 6 | Challenge record, decisions, limitations and improvement plan. — Did the analysis affect strategy, capital or risk decisions?

## Table 4
Phase | Core activity | First-cycle evidence
Design | Approve organisational boundary, method, factor and GWP policy, Scope 2 basis and category screen. | Boundary memo, methodology and factor register.
Source mapping | Identify source systems, owners, periods, units, access, retention and gaps. | Source and evidence register.
Dry run | Calculate Scope 1, Scope 2 and relevant Scope 3 categories using prior or interim data. | Calculation model, estimates, exception log and review.
Control test | Recalculate samples, reconcile activity data, challenge estimates and test change controls. | Control testing and remediation record.
Year-end close | Apply cut-off, late-data estimates, final review and management certification. | Locked inventory, representation and final disclosure table.

## Table 5
Control family | Example first-cycle control | Testing evidence
Governance | Quarterly status, critical judgement and unresolved finding review by the steering committee. | Papers, minutes, decisions and escalation.
Data | Source-system extract reconciled to approved population and period; manual adjustments reviewed. | Reconciliation, sample and exception log.
Method / model | Method, factor, scenario or model change approved before use. | Change request, version comparison and approval.
Narrative | Material claims traced to evidence and reviewed for balance, scope and consistency. | Claim ledger and reviewer comments.
Connected information | Climate metrics and narrative reconciled to financial statements, NFSIS, SECR and other public information. | Cross-framework reconciliation and conflict log.
Release | Final documents, cross-references, URLs, timestamps and archived evidence checked. | Release certificate and immutable archive.

## Table 6
Mock request | Expected response | Typical finding
Show why a climate risk is material and how it affects prospects. | Risk record, materiality rationale, transmission path, finance link and approval. | Risk description exists, but prospects and decision-useful effect are unsupported.
Reproduce the Scope 3 total and explain category completeness. | Category screen, source data, factors, calculations, estimates and review. | Categories were excluded because data were difficult rather than after relevance assessment.
Support the resilience conclusion. | Scenario scope, assumptions, results, options, capacity, triggers, limitations and governance. | Actions are listed, but capacity to adapt is not assessed.
Support anticipated financial effects. | Model or range, assumptions, affected line items, reconciliation and uncertainty. | Narrative is disconnected from budgets and financial statements.
Explain the compliance statement and provision use. | Completed matrix, provision analysis, legal/technical review and board paper. | IFRS relief wording was copied without checking final UK conditions.

## Common implementation mistakes
Common implementation mistakes
Mistake | Why it happens | Correction
The programme begins with a report template. | Drafting appears tangible and hides unresolved methods. | Begin with reporting basis, requirements, risks, boundaries and evidence.
All workstreams have the same deadline. | The plan ignores dependencies. | Sequence risks before scenarios and financial effects; start GHG early; test controls before drafting is final.
“Complete” means the number exists. | Project status is not evidence readiness. | Apply scope, method, data, control, disclosure and approval gates.
Scope 3 is deferred until year-end. | Teams assume it is simply a supplier-data exercise. | Screen all 15 categories early and design estimates and improvement plans.
Assurance is requested after board approval. | The team treats review as a badge rather than a challenge process. | Run a mock evidence request and close findings before governance approval.
Relief wording is copied from IFRS S2. | UK amendments and binding-route conditions are not checked. | Use the final UK text and approve provision use separately.