## About
London Reporting Academy
Guide | How to Prepare a UK SRS S2 Climate Report: Complete Step-by-Step Guide
Source | https://reporting.academy/en/knowledge-hub/disclosure-guides/uk-srs-s2/uk-srs-s2-cycle-controls-and-assurance/how-to-prepare-a-uk-srs-s2-climate-report-complete-step-by-step-guide/
Standard edition | UK SRS S1 and UK SRS S2, February 2026; current regulatory status reviewed 2 August 2026
Reviewed by | Dr Ross Kurinko
Last reviewed | 2026-08-11
How to use | Work through each sheet with the owners named in the guide. The status and owner columns are deliberately empty — they are yours to fill in and keep as evidence.
Status | Educational guidance from London Reporting Academy. It is not a substitute for the standard itself, and it is not issued or endorsed by the standard setter.

## Final publication checklist
Final publication checklist
From: How to Prepare a UK SRS S2 Climate Report: Complete Step-by-Step Guide
# | Check | Status | Owner | Evidence / note
1 | Reporting basis, entity, period, location and intended claim are approved.
2 | Material climate risks and opportunities are complete, evidenced and linked to prospects.
3 | Governance, strategy, risk management, metrics and targets answer the S2 objectives.
4 | Scenario analysis is proportionate, company-specific and connected to resilience conclusions.
5 | Current and anticipated financial effects are quantitatively or qualitatively explained with line-item links.
6 | Scope 1-3, industry metrics and targets have methods, controls, comparatives and limitations.
7 | Reliefs are eligible, disclosed, locally permitted and reflected in claim wording.
8 | Cross-references are precise and available with the annual report.
9 | Finance, risk, legal/company secretarial, internal audit or assurance-readiness review and board approval are complete.
10 | Version, reviewer, source register, changelog and update triggers are retained.

## The 12-month implementation pla
The 12-month implementation plan
Months | Primary work | Key output — Decision gate
1-2 | Basis, scope, project governance and gap assessment. | Approved project charter, S1/S2 disclosure matrix, regulatory watch and responsibility map. — Audit committee or sponsor approves basis and resources.
3-4 | Risk-opportunity identification, materiality, horizons, business-model and value-chain mapping. | Controlled climate risk-opportunity register and materiality decisions. — Management agrees the material set and analysis scope.
5-6 | Governance evidence, strategy responses, transition-plan disclosure and scenario-analysis design. | Governance evidence pack, scenario brief and strategy linkage. — Board or executive committee challenges assumptions and scenario scope.
7-8 | Current and anticipated financial effects, GHG inventory, Scope 3 and financed-emissions work. | Finance bridge, GHG methodology, data-gap log and relief recommendation. — CFO and risk/data owners approve methods and limitations.
9-10 | Industry metrics, targets, drafting, annual-report location and cross-references. | First complete draft, metric dictionary, target register and cross-reference map. — Technical, finance and legal review clears substantive gaps.
11-12 | Dry run, evidence testing, internal audit/assurance readiness, board approval and publication. | Final disclosures, evidence index, representations, approval record and update plan. — Board or authorised committee approves publication and claim wording.

## Step 8 - quantify and explain f
Step 8 - quantify and explain financial effects
Work area | Questions for finance | Evidence
Current effects | What affected revenue, costs, assets, liabilities or cash flows in the reporting period? | Management accounts, incident costs, insurance, impairment/provision papers, capex and operating data.
Anticipated position | How could assets, liabilities, investments, disposals and funding change over each horizon? | Budgets, strategic plan, capex pipeline, financing plan and scenario outputs.
Anticipated performance and cash flows | How could demand, pricing, operating costs, damage, adaptation or mitigation change performance? | Forecasts, sensitivities, business cases and treasury assumptions.
Quantification relief | Are effects separately identifiable and useful? Are skills, capabilities and resources sufficient? | Documented paragraph 19-20 assessment, qualitative line-item links and combined effects where useful.

## Common first-cycle failures
Common first-cycle failures
Failure | Early warning sign | Preventive control
Starting with report drafting | Long narrative but no controlled R/O register or finance bridge. | Complete basis, register and evidence architecture before drafting.
Scenario work isolated from finance | Scenarios use variables that never enter planning or financial-effects analysis. | Joint scenario-finance design and sign-off.
Scope 3 treated as a year-end calculation | Category screening, supplier data and estimation methods are unresolved late in the cycle. | Launch category and data-quality work in months 3-4.
Industry metrics selected from one peer | Cherry-picked metrics and weak comparability rationale. | Use a source hierarchy and documented selection criteria.
Board approval focuses on wording only | No paper on judgements, reliefs, evidence gaps or financial consistency. | Use a structured board decision pack.
Cross-referenced report published later | Critical S2 information is unavailable with the annual report. | Apply same-time publication controls under S1 64 and B45-B47.